## Munka1
Task | Start Date | Deadline | Duration
Flight System Acceptance Test | 2018-09-19 | 2018-09-23 | 4
Temperature Sensor Calibration | 2018-09-23 | 2018-09-30 | 7
Backup Tracker LDO Upgrade | 2018-09-19 | 2018-09-30 | 11
Backup Tracker SD Card Integration | 2018-09-23 | 2018-10-07 | 14
Backup Tracker Capsule Manufacturing | 2018-09-26 | 2018-10-07 | 11
Payload Train Integration Test | 2018-09-30 | 2018-10-07 | 7
Payload Train Final Integration | 2018-10-07 | 2018-10-14 | 7
Preliminary Flight Window | 2018-10-20 | 2018-10-28 | 8
Send Flight Plan to FAA | 2018-10-09 | 2018-10-15 | 6
Prepare Launch Equipment | 2018-10-14 | 2018-10-20 | 6
Prepare Recovery Equipment | 2018-10-14 | 2018-10-20 | 6
Purchase Helium | 2018-10-07 | 2018-10-19 | 12
Select Primary Station Location | 2018-10-07 | 2018-10-19 | 12
Brief Launch Team | 2018-10-14 | 2018-10-19 | 5
Brief Recovery Team | 2018-10-14 | 2018-10-20 | 6
Organize Launch Event | 2018-10-07 | 2018-10-16 | 9